## Cover
OpenText LRE Upgrade ¦ 25.1 → 26.1
Sequence of Events (SOE) — Installation & Upgrade Runbook
Document Date | 24 February 2026
Upgrade Version | 25.1 → 26.1
Prepared By | <Your Name / Team>
Approved By | <Manager / Change Manager>
Change Ref # | <ITSM Change # / CR-XXXXX>
Workbook Contents
Prerequisites | Hardware, software, network, and account requirements before starting.
Pre-Upgrade Checks | Run diagnostic script on every machine. Confirm all checks PASS.
LRE Server Upgrade | Step-by-step guide to upgrade the LRE Server (script 01).
Host Upgrades | Upgrade Controller, Data Processor, and Load Generator hosts (scripts 02–04).
Post-Upgrade Verify | Health checks and browser tests to confirm successful upgrade (script 05).
Backout Plan | Step-by-step rollback procedure if the upgrade must be reversed.
⚠ Always obtain Change Advisory Board (CAB) approval before executing this runbook in production.

## Prerequisites
PREREQUISITES — LRE 25.1 → 26.1 Upgrade
# | Category | Requirement | Detail / Acceptance Criteria | Status
ACCESS & ACCOUNTS
1 | Access & Accounts | Local Administrator rights | Must run all PowerShell upgrade scripts under a local admin account. Right-click → 'Run as Administrator'. | Pending
2 | Access & Accounts | Network share access (read) | Account must have read access to \\fileserver\LRE_26.1 from every upgrade target machine. | Pending
3 | Access & Accounts | DB Admin credentials | SQL Server 'sa' (or equivalent DBA) credentials required. Kept in upgrade_config.ps1 or entered at prompt. | Pending
4 | Access & Accounts | DB Application user credentials | lre_user (or equivalent) credentials required for LRE databases. | Pending
5 | Access & Accounts | LRE System user credentials | IUSR_METRO (or custom domain user) password required. Must match on ALL nodes. | Pending
INSTALLER MEDIA
6 | Installer Media | 26.1 installer share populated | \\fileserver\LRE_26.1\Setup\En\setup_server.exe and setup_host.exe must exist. | Pending
7 | Installer Media | OneLG installer present | \\fileserver\LRE_26.1\Standalone Applications\SetupOneLG.exe must exist. | Pending
8 | Installer Media | Prerequisites in share | Share must contain: dotnet48\ndp48-*.exe, dotnet_hosting\dotnet-hosting-8.0.*.exe, vc2022_redist_x86\vc_redist.x86.exe, vc2022_redist_x64\vc_redist.x64.exe | Pending
9 | Installer Media | Vendor UserInput.xml present | \\fileserver\LRE_26.1\Setup\Install\Server\UserInput.xml (merge template used by script 01). | Pending
SOFTWARE & OS
10 | Software & OS | Current version confirmed = 25.1 | Run 00_PreUpgradeChecks.ps1 on every machine. 'LRE Version is 25.1' check must PASS. | Pending
11 | Software & OS | Windows OS (English locale) | All upgrade targets must be Windows Server with en-* locale. Non-English locales may cause silent installer issues. | Pending
12 | Software & OS | IIS installed (LRE Server only) | W3SVC service must be present on the LRE Server machine before running script 01. | Pending
13 | Software & OS | No pending Windows reboots | Run 00_PreUpgradeChecks.ps1 — 'No Pending Reboot' must PASS. Reboot and re-run if needed. | Pending
DISK & NETWORK
14 | Disk & Network | ≥ 20 GB free disk space on C:\ | Each target machine (Server, Controller, DP, LG) must have at least 20 GB free on C:\. | Pending
15 | Disk & Network | C:\LRE_UpgradeLogs directory writable | Script creates C:\LRE_UpgradeLogs automatically. Confirm the account has write access to C:\. | Pending
16 | Disk & Network | All machines can reach installer share | Test from each machine: Test-Path '\\fileserver\LRE_26.1' should return True. | Pending
17 | Disk & Network | LRE Server FQDN resolves | lre.yourdomain.com (or your IisSecureHostName) must resolve from all host machines. | Pending
DATABASE
18 | Database | Database backups taken | Confirm DBA has backed up: LRE_LAB, LRE_ADMIN, LRE_SITE databases BEFORE starting upgrade. | Pending
19 | Database | SQL Server accessible | sql-server-01:1433 (or your DbServerHost:DbServerPort) must be reachable from the LRE Server. | Pending
SECURITY & ENCRYPTION
20 | Security | Secure Passphrase agreed (≥ 12 chars) | A single passphrase must be agreed upon BEFORE upgrade. It must be used identically on ALL nodes. | Pending
21 | Security | Encryption key (LW_CRYPTO_INIT_STRING) known | CryptoKey value must be identical across Server, Controller, DP, and LG. Obtain from current pcs.config if needed. | Pending
22 | Security | TLS certificate available | A valid SSL certificate for lre.yourdomain.com must be in the Windows Certificate Store (or .pfx file ready for import). | Pending
CHANGE MANAGEMENT
23 | Change Management | CAB approval obtained | A Change Request must be approved by the Change Advisory Board before executing in production. | Pending
24 | Change Management | Maintenance window scheduled | Coordinate downtime window with all stakeholders. Estimate: 2–4 hours for a single-server environment. | Pending
25 | Change Management | Rollback decision point agreed | Agree in advance: at what stage will the team decide to roll back? (Recommendation: if server upgrade fails at Phase 7.) | Pending

## Pre-Upgrade Checks
PRE-UPGRADE CHECKS — Run on EVERY machine before upgrade
# | Check | How to Verify / Expected Result | Machine(s) | Result
▶ Script: .\00_PreUpgradeChecks.ps1 (run elevated on each machine — Server, Controller, Data Processor, Load Generator)
1 | Administrator Privileges | Run script elevated (right-click → Run as Administrator). Script self-checks and reports PASS/FAIL. | All machines | Pending
2 | Operating System | Script reports Windows OS and build number. Must be Windows Server. | All machines | Pending
3 | System Locale = English | Locale must show 'en-*'. Non-English may cause installer issues. | All machines | Pending
4 | No Pending Reboot | Must show 'No pending reboot'. If FAIL: reboot the machine and re-run checks. | All machines | Pending
5 | Installed LRE Version = 25.1 | Registry check confirms current installation is 25.1. Script exits with error if not 25.1. | All machines | Pending
6 | Disk Space ≥ 20 GB free on C:\ | Must show PASS. Free up disk space if FAIL before proceeding. | All machines | Pending
7 | .NET Framework 4.8 | Registry Release value must be ≥ 528040. Script will install it in Phase 5 if missing. | All machines | Pending
8 | .NET Core Hosting 8.x | dotnet --list-runtimes shows Microsoft.AspNetCore.App 8.x. Script installs if missing. | All machines | Pending
9 | IIS Installed (W3SVC) | W3SVC service must be present. Mandatory for LRE Server machine only. | LRE Server | Pending
10 | LRE Services Status | Script reports current state of IIS, Backend, Alerts, Agent, Remote Mgmt services. Note down states. | All machines | Pending
11 | Installer Share Accessible | \\fileserver\LRE_26.1 must return True. If FAIL: check share path and permissions. | All machines | Pending
12 | setup_server.exe / setup_host.exe / SetupOneLG.exe found | All three installer executables must be found. If FAIL: verify installer media in the share. | All machines | Pending
13 | No Installer Processes Running | No msiexec / setup processes must be running. Kill any stale installer processes if FAIL. | All machines | Pending
14 | Database Backups Confirmed | Manual step — contact DBA and get written confirmation that LRE_LAB, LRE_ADMIN, LRE_SITE are backed up. | LRE Server | Pending
15 | upgrade_config.ps1 Updated | Open config\upgrade_config.ps1 and confirm all <-- UPDATE THIS fields are filled in correctly. | Any machine | Pending
✔ Proceed to LRE Server Upgrade sheet only when ALL checks are PASS on all machines.

## LRE Server Upgrade
LRE SERVER UPGRADE ¦ Script: 01_Upgrade_LREServer.ps1
Step | Action | Detail / Command | Note / Expected Result | Status
PHASE 1 — PRE-UPGRADE CHECKS (Automated)
1.1 | Confirm installer share is accessible | Script automatically checks that \\fileserver\LRE_26.1 is reachable and setup_server.exe is found. | Script exits with ERROR if share or EXE not found. Fix path in upgrade_config.ps1. | Auto
1.2 | Verify current version = 25.1 | Script reads Windows registry and confirms installed version matches 25.1. | Script exits with ERROR if version doesn't match. Do not bypass. | Auto
1.3 | Check disk space ≥ 20 GB | Script checks free space on C:\. Fails if < 20 GB free. | Free up disk space before re-running if this fails. | Auto
1.4 | Check no pending reboot | Script checks pending reboot registry keys. | Reboot the machine and re-run script if this fails. | Auto
PHASE 2 — GATHER CREDENTIALS (Interactive prompt)
2.1 | Enter DB Admin password | Script prompts: Enter DB Admin password for 'sa' | Type securely at the prompt. Leave blank in config to always prompt. | Manual
2.2 | Enter DB User password | Script prompts: Enter DB User password for 'lre_user' | Type securely at the prompt. | Manual
2.3 | Enter System User password | Script prompts: Enter System User password for 'IUSR_METRO' | Must match password for the Windows service account. | Manual
2.4 | Enter Secure Passphrase | Script prompts: Enter Secure Communication Passphrase (min 12 chars) | Must be ≥ 12 alphanumeric characters. Note it down — must be the same on ALL nodes. | Manual
PHASE 3 — DATABASE BACKUP CONFIRMATION (Manual confirm)
3.1 | Confirm database backups | Script displays DB server/database names and asks: 'I confirm that database backups are complete. Continue?' | Type Y to proceed. If DBA has not confirmed backups, type N and wait for confirmation. | Manual
PHASE 4 — STOP SERVICES (Automated)
4.1 | Stop IIS | Script runs: iisreset /stop | IIS (W3SVC) is stopped. LRE web UI becomes unavailable — expected. | Auto
4.2 | Stop LRE Backend Service | Script stops LREBackend / OpenTextLREBackend service. | Service names checked in order. Warning is logged if service not found (may already be stopped). | Auto
4.3 | Stop LRE Alerts Service | Script stops LREAlerts / OpenTextLREAlerts service. | Warning if not found — not critical. | Auto
4.4 | [CLUSTERED ONLY] Stop services on ALL other nodes | If you have multiple LRE Servers (cluster): manually stop IIS + Backend + Alerts on EVERY other node BEFORE running the installer on any node. | Failure to do this in a cluster will cause data corruption. | Manual (if clustered)
PHASE 5 — INSTALL PREREQUISITES (Automated)
5.1 | Install .NET Framework 4.8 | Script runs ndp48-x86-x64-allos-enu.exe /q /norestart (if not already installed). | Exit codes 0, 3010, 1641 = success. Exit 3010 = reboot needed after install. | Auto
5.2 | Install .NET Core Hosting 8.x | Script runs dotnet-hosting-8.0.17-win.exe /quiet | Provides ASP.NET Core runtime required by LRE 26.1 backend. | Auto
5.3 | Install VC++ Redistributable x86 & x64 | Script runs vc_redist.x86.exe and vc_redist.x64.exe /quiet /norestart | Required C++ runtime libraries for LRE components. | Auto
PHASE 6 — PREPARE UserInput.xml (Automated)
6.1 | Generate UserInput.xml | Script copies vendor's UserInput.xml from the share and merges your config values into it (DB server, credentials, passphrase, cert, paths). | A timestamped XML is written to C:\LRE_UpgradeLogs\UserInput\. Passwords are NOT logged. | Auto
PHASE 7 — RUN LRE SERVER INSTALLER (Automated with confirm)
7.1 | Confirm installer launch | Script asks: 'About to run LRE Server upgrade from setup_server.exe. Continue?' | Type Y to launch. This starts the in-place upgrade — the existing 25.1 installation is upgraded to 26.1. | Manual
7.2 | Silent installer runs (up to 90 min) | setup_server.exe /s USER_CONFIG_FILE_PATH="...xml" INSTALLDIR="C:\Program Files\OpenText\LRE" | DO NOT interrupt. A separate installer log is written to C:\LRE_UpgradeLogs\. Expected exit code: 0 (success) or 3010 (reboot needed). | Auto
7.3 | Check exit code | 0 = Success. 3010 = Reboot required. 1602 = Cancelled. 1603 = Fatal error (check installer log). | If exit code is 1603 or unexpected: check C:\LRE_UpgradeLogs\LREServer_Installer_*.log for details before retrying. | Auto
PHASE 8 — POST-INSTALL VERIFICATION (Automated)
8.1 | Read Configuration Wizard log | Script reads last 30 lines of configurationWizardLog_pcs.txt from the install directory. | Logged to C:\LRE_UpgradeLogs\. Review if ERROR / FAIL / exception keywords are found. | Auto
PHASE 9 — START SERVICES (Automated)
9.1 | Start IIS | Script runs: iisreset /start | Waits 10 seconds for full IIS initialisation. | Auto
9.2 | Start LRE Backend Service | Script starts LREBackend / OpenTextLREBackend. | Service start confirmed in log. | Auto
9.3 | Start LRE Alerts Service | Script starts LREAlerts / OpenTextLREAlerts. | Service start confirmed in log. | Auto
PHASE 10 — CAPTURE PUBLIC KEY (Automated)
10.1 | Wait 30 seconds for services to initialise | Script pauses 30 s before querying the REST API. | Allow time for LRE backend to fully start. | Auto
10.2 | Retrieve Public Key via REST API | Script calls: GET http://localhost/Admin/rest/v1/configuration/getPublicKey | If successful, key is written to \\fileserver\LRE_26.1\PublicKey.txt and to C:\LRE_UpgradeLogs\PublicKey.txt. | Auto
10.3 | Fallback — read from pcs.config | If REST fails: script reads key from C:\Program Files\OpenText\LRE\dat\pcs.config | If both methods fail: retrieve manually from the URL above or the Configuration Wizard 'Finish' page. | Auto
10.4 | [IF MANUAL] Provide Public Key to host scripts | If key could not be auto-captured: set PublicKeyValue in upgrade_config.ps1 manually before running scripts 02–04. | The Public Key is required by Controller, Data Processor, and Load Generator upgrade scripts. | Manual (if needed)
PHASE 11 — CONFIG CONSISTENCY & VERSION CHECK (Automated)
11.1 | Verify pcs.config and appsettings.json | Script checks C:\Program Files\OpenText\LRE\dat\pcs.config and C:\LRE_Repository\system_config\appsettings.json for correct SystemUserName. | WARN logged if user doesn't match. Review manually if WARNING. | Auto
11.2 | Confirm installed version = 26.1 | Script re-reads registry and confirms new version is 26.1. | WARN if version doesn't match expected. Log the actual version. | Auto
11.3 | Clean up temp UserInput.xml | Script deletes C:\LRE_UpgradeLogs\UserInput\Server_UserInput_*.xml (contains passwords). | Confirm file is deleted. If not deleted automatically, delete manually. | Auto
COMPLETE — LRE Server Upgrade Finished
✔ | Verify LRE UI is accessible | Open browser: https://lre.yourdomain.com/LRE/ | LRE login page must load. If not: check IIS and backend service status. | Manual
✔ | Proceed to Host Upgrades sheet | Run 02_Upgrade_Controller.ps1, then 03_Upgrade_DataProcessor.ps1, then 04_Upgrade_LoadGenerator.ps1 on respective machines. | Do NOT skip scripts. Each host depends on the Public Key written by script 01. | Next Step

## Host Upgrades
HOST UPGRADES ¦ Scripts: 02 (Controller) · 03 (Data Processor) · 04 (Load Generator)
▶ Prerequisite: 01_Upgrade_LREServer.ps1 must have completed successfully and PublicKey.txt must be written to the installer share.
Step | Host Type | Action | Detail / Command | Machine(s) | Status
CONTROLLER — 02_Upgrade_Controller.ps1
C-1 | Controller | Pre-flight checks | Script checks installer share, confirms current version = 25.1, disk space, pending reboot. | Each Controller host | Pending
C-2 | Controller | Enter credentials at prompt | Prompts for: DB Admin password, DB User password, System User password, Secure Passphrase, Public Key (if not in config). | Each Controller host | Pending
C-3 | Controller | Stop services (auto) | Script stops LoadRunner Agent Service and Remote Management Agent on this host. | Each Controller host | Pending
C-4 | Controller | Install prerequisites (auto) | Installs .NET 4.8, .NET Core Hosting 8.x, VC++ Redist x86/x64 if not already present. | Each Controller host | Pending
C-5 | Controller | Prepare UserInput.xml (auto) | Merges config values into vendor's HostUserInput.xml. Written to C:\LRE_UpgradeLogs\UserInput\. | Each Controller host | Pending
C-6 | Controller | Run host installer (auto ~60 min) | setup_host.exe /s USER_CONFIG_FILE_PATH="...xml" INSTALLDIR="C:\Program Files\OpenText\Performance Center Host" | Each Controller host | Pending
C-7 | Controller | Start services (auto) | Script restarts LoadRunner Agent Service and Remote Management Agent after successful install. | Each Controller host | Pending
C-8 | Controller | Verify version = 26.1 | Registry check confirms new version. Log is written to C:\LRE_UpgradeLogs\Controller_Upgrade_*.log. | Each Controller host | Pending
DATA PROCESSOR — 03_Upgrade_DataProcessor.ps1
D-1 | Data Processor | Pre-flight checks | Same as Controller: share access, version check (25.1), disk space, pending reboot. | Each DP host | Pending
D-2 | Data Processor | Enter credentials at prompt | Same credential prompts as Controller. | Each DP host | Pending
D-3 | Data Processor | Stop services (auto) | Stops Agent and Remote Mgmt Agent. | Each DP host | Pending
D-4 | Data Processor | Install prerequisites (auto) | Same prerequisite set as Controller. | Each DP host | Pending
D-5 | Data Processor | Run host installer (auto ~60 min) | setup_host.exe /s with DP-specific UserInput.xml values. | Each DP host | Pending
D-6 | Data Processor | Start services & verify (auto) | Agent and Remote Mgmt started. Version check to 26.1. Log written. | Each DP host | Pending
LOAD GENERATOR — 04_Upgrade_LoadGenerator.ps1
L-1 | Load Generator | Pre-flight checks | Checks share, confirms OneLG version = 25.1, disk space, pending reboot. | Each LG host | Pending
L-2 | Load Generator | Determine installer method | Script auto-detects: uses SetupOneLG.exe if found, falls back to OneLG_x64.msi. | Each LG host | Pending
L-3 | Load Generator | Enter credentials at prompt | Prompts for System User password and Secure Passphrase. | Each LG host | Pending
L-4 | Load Generator | Stop LoadRunner Agent Service (auto) | Stops magentservice / LoadRunnerAgentService before install. | Each LG host | Pending
L-5 | Load Generator | Install prerequisites (auto) | Installs .NET 4.8, .NET Core Hosting, VC++ Redist. | Each LG host | Pending
L-6 | Load Generator | Run OneLG installer (auto ~60 min) | SetupOneLG.exe /s with UserInput.xml OR msiexec /i OneLG_x64.msi /qn with properties. | Each LG host | Pending
L-7 | Load Generator | Start Agent & verify (auto) | Restarts LoadRunner Agent Service. Verifies version = 26.1. | Each LG host | Pending
ALL HOSTS COMPLETE — Run Post-Upgrade Verification
✔ | All | Proceed to Post-Upgrade Verify sheet | Run 05_PostUpgradeVerify.ps1 on every machine to confirm full environment health. | All machines | Next Step

## Post-Upgrade Verify
POST-UPGRADE VERIFICATION ¦ Script: 05_PostUpgradeVerify.ps1
▶ Run on EACH machine: .\05_PostUpgradeVerify.ps1 (elevated PowerShell — auto-detects Server / Controller / DP / LG)
# | Verification Check | Expected Result / How To Verify | Machine(s) | Result
AUTOMATED — Script 05_PostUpgradeVerify.ps1 (runs all checks below)
1 | Version = 26.1 | Registry shows installed version 26.1. Script reports PASS. | All machines | Pending
2 | IIS (W3SVC) Running | Service status = Running. Script reports PASS. | LRE Server | Pending
3 | LRE Backend Service Running | LREBackend / OpenTextLREBackend = Running. | LRE Server | Pending
4 | LRE Alerts Service Running | LREAlerts / OpenTextLREAlerts = Running. | LRE Server | Pending
5 | LoadRunner Agent Service Running | magentservice / LoadRunnerAgentService = Running. | Controller, DP, LG | Pending
6 | Remote Management Agent Running | AlAgent / RemoteManagementAgent = Running. | Controller, DP, LG | Pending
7 | LRE Web Application Accessible | Script tests https://<FQDN>/LRE/ — expects HTTP 200 / 302. | LRE Server | Pending
8 | pcs.config User Consistency | C:\Program Files\OpenText\LRE\dat\pcs.config contains SystemUserName (IUSR_METRO). | LRE Server | Pending
9 | appsettings.json User Consistency | C:\LRE_Repository\system_config\appsettings.json contains SystemUserName. | LRE Server | Pending
10 | lts.config User Consistency | C:\Program Files\OpenText\Performance Center Host\dat\lts.config contains SystemUserName. | Controller, DP | Pending
11 | OneLG Config File Exists | C:\Program Files\OpenText\OneLG\dat\lts.config (or br_lnch_server.cfg) found. | Load Generator | Pending
12 | No Pending Reboot | No pending reboot registry keys. Reboot and re-verify if FAIL. | All machines | Pending
13 | Temp UserInput.xml Files Cleaned Up | C:\LRE_UpgradeLogs\UserInput\ contains no *.xml files with credentials. | All machines | Pending
14 | No Recent LRE Event Log Errors | No LRE/OpenText/LoadRunner Error events in Application log in last 2 hours. | All machines | Pending
MANUAL CHECKS — Browser & Functional
15 | Log in to LRE UI | Open https://lre.yourdomain.com/LRE/ in browser. Log in as admin. Confirm landing page loads. | LRE Server | Pending
16 | Check Administration > About | Verify version shown = 26.1 in the LRE Administration module. | LRE Server | Pending
17 | Verify all host machines appear in Administration | In LRE Administration > Hosts, confirm Controllers, DPs, and LGs are listed and show 'Connected'. | LRE Server (browser) | Pending
18 | Run a smoke test scenario | Run a short / known-good test scenario to confirm LRE can allocate hosts, run a load test, and process results. | LRE Server (browser) | Pending
19 | Confirm Public Key file on share | Check \\fileserver\LRE_26.1\PublicKey.txt exists and is non-empty. | Any machine | Pending
20 | Archive upgrade logs | Copy C:\LRE_UpgradeLogs\ from every machine to a central archive location. | All machines | Pending
21 | Close Change Request | Update ITSM Change Request with completion status, evidence (log paths), and any deviations from this SOE. | Change Manager | Pending
✔ All checks PASS + smoke test complete = Upgrade Successful. Update the Change Request and close.

## Backout Plan
BACKOUT PLAN — LRE 25.1 → 26.1 Upgrade Rollback
WHEN TO INVOKE THIS PLAN: • LRE Server installer exits with code 1603 (Fatal Error) AND cannot be resolved within the maintenance window. • Post-install services fail to start after multiple attempts. • LRE web UI is inaccessible after upgrade and the root cause cannot be identified quickly. • Business impact is unacceptable and rolling forward is not feasible within the window. DECISION AUTHORITY: The Change Manager (or designated technical lead) must formally declare 'Rollback' before executing these steps.
Step | Action | Detail / Command | Machine(s) | Owner
IMMEDIATE ACTIONS — Stop the upgrade
B-1 | Declare Rollback | Change Manager verbally declares rollback. All team members stop any in-progress installer steps. | All | Change Manager
B-2 | Do NOT reboot any machine | Avoid reboots until the rollback plan is underway. Reboots during a partial install may leave machines unbootable. | All | All team
B-3 | Document the failure point | Note exactly which Phase/Step failed, the exit code, and the last lines of the installer log: C:\LRE_UpgradeLogs\LREServer_Installer_*.log | LRE Server | Tech Lead
STOP ALL SERVICES ON ALL NODES
B-4 | Stop LRE Services (Server) | Run: iisreset /stop then stop LREBackend and LREAlerts services. net stop LREBackend net stop LREAlerts | LRE Server | Tech Lead
B-5 | Stop LRE Services (Hosts) | On each Controller, DP, LG: net stop magentservice net stop AlAgent | All hosts | Tech Lead
RESTORE DATABASE FROM BACKUP
B-6 | Contact DBA — restore databases | DBA restores LRE_LAB, LRE_ADMIN, LRE_SITE from the pre-upgrade backup taken in Phase 3. | SQL Server | DBA
B-7 | Confirm database restore complete | DBA confirms all three databases are restored and accessible at the same connection strings (DbServerHost:DbServerPort). | SQL Server | DBA
UNINSTALL 26.1 — RESTORE 25.1
B-8 | Uninstall LRE 26.1 from LRE Server | Option A (preferred): Use Windows Add/Remove Programs to uninstall LRE 26.1. Option B: Run the 26.1 installer in repair/remove mode if available. Option C: msiexec /x {ProductCode} /qn (find product code in registry: HKLM\SOFTWARE\Microsoft\Windows\CurrentVersion\Uninstall) | LRE Server | Tech Lead
B-9 | Reinstall LRE 25.1 from original media | Run the 25.1 setup_server.exe with the original 25.1 UserInput.xml (retrieve from your pre-upgrade archive or backup). | LRE Server | Tech Lead
B-10 | Uninstall 26.1 from Host machines (if upgraded) | Repeat uninstall on any Controller/DP/LG that completed the 26.1 upgrade before rollback was declared. Use Add/Remove Programs or msiexec /x. | Upgraded hosts | Tech Lead
B-11 | Reinstall LRE 25.1 on Host machines | Run the original 25.1 setup_host.exe / SetupOneLG.exe on each host that was uninstalled in B-10. | Upgraded hosts | Tech Lead
RESTORE CONFIGURATION FILES
B-12 | Restore pcs.config from backup | Copy backed-up pcs.config to C:\Program Files\OpenText\LRE\dat\pcs.config on the LRE Server. | LRE Server | Tech Lead
B-13 | Restore appsettings.json from backup | Copy backed-up appsettings.json to C:\LRE_Repository\system_config\appsettings.json. | LRE Server | Tech Lead
B-14 | Restore lts.config on hosts (if applicable) | Copy pre-upgrade lts.config to C:\Program Files\OpenText\Performance Center Host\dat\ on each host. | Controller, DP | Tech Lead
RESTART SERVICES AND VALIDATE
B-15 | Start LRE Services (Server) | Run: iisreset /start net start LREBackend net start LREAlerts | LRE Server | Tech Lead
B-16 | Start LRE Services (Hosts) | On each host: net start magentservice net start AlAgent | All hosts | Tech Lead
B-17 | Verify LRE UI is accessible on 25.1 | Open https://lre.yourdomain.com/LRE/ and confirm: - Login page loads - Administration > About shows version 25.1 - All hosts appear as Connected | LRE Server | Tech Lead
B-18 | Run smoke test on 25.1 | Execute a known-good short test scenario to confirm LRE is fully functional at 25.1. | LRE Server | Test Lead
COMMUNICATION & CLOSE-OUT
B-19 | Notify stakeholders | Inform all stakeholders that the upgrade was rolled back and LRE is restored to 25.1. | All | Change Manager
B-20 | Update Change Request | Update ITSM Change Request with: - Failure point and reason - Rollback steps taken - Current state (25.1 restored) - Log file paths - Next planned upgrade window | All | Change Manager
B-21 | Conduct Post-Incident Review | Schedule a PIR (Post-Incident Review) within 5 business days. Review failure root cause, adjust SOE if needed. | All | Change Manager
⚠ Rollback complete when: LRE 25.1 UI is accessible, smoke test passes, DBA confirms databases restored, Change Request updated.