## SOE - Server Installation Steps
# | Phase | Task | Executor | Target | Detailed Steps | Status | Purpose | Completed | Notes
Start - Post Installation
32 | Post-Installation | Configure TLS/SSL - Web.config | LRE Admin | Primary LRE Server | 1. Navigate to "D:\LREServer\PCS\Web.config" 2. Create backup copy of the "web.config" file 3. Copy "web.config-for_ssl" from "D:\LREServer\conf\httpsConfigFiles" to "D:\LREServer\PCS" | Pending | Enables HTTPS | No
33 | Post-Installation | Configure TLS/SSL - Internal URL | LRE Admin | Primary LRE Server | 1. Open "D:\LREServer\dat\PCS.config" 2. Update internalUrl attribute to use HTTPS: internalUrl="https://devecpvm027794.webdev.banksvcs.net:12001" | Pending | Configures secure communication | No
34 | Post-Installation | Configure TLS/SSL - Secure Host | LRE Admin | Primary LRE Server | 1. Edit "D:\LREServer\dat\PCS.config" 2. Change ltopIsSecured parameter to true: <PCSSettings ltopPortNumber="8731" ltopIsSecured="true" StartRunMaxRetry="3" DataProcessorPendingTimeoutMinutes="2880"/> | Pending | Enables TLS for host communication | No
35 | Post-Installation | Update CA Certificates | LRE Admin | Primary LRE Server | 1. Navigate to "\\rbsres01\grpareas\LRE\LREadmin\LRE_CERTS" 2. Copy content of "lre_dev_cacert.cer" file 3. Replace content in "D:\LREServer\dat\cert\verify\cacert.cer" | Pending | Updates CA certificates with RBS Global G1 Root Proving CA | No
36 | Post-Installation | Update TLS Certificates | LRE Admin | Primary LRE Server | 1. Navigate to "\\rbsres01\grpareas\LRE\LREadmin\LRE_CERTS" 2. Copy content of server-specific certificate (e.g., lre_dev_devecpvm027794_iis_dev.cer) 3. Replace content in "D:\LREServer\dat\cert\cert.cer" | Pending | Updates TLS certificate and private key | No
37 | Post-Installation | Verify Certificates | LRE Admin | Primary LRE Server | Run command: "D:\LREServer\bin\gen_cert.exe -verify" | Pending | Confirms certificates are valid | No
38 | Post-Installation | Configure AWS Regions | LRE Admin | Primary LRE Server | 1. Edit "D:\LREServer\LRE_BACKEND\appsettings.defaults.json" 2. Add ActiveRegions section under AWS: "AWS": { "ActiveRegions": [ "eu-west-2" ] } | Pending | Limits available AWS regions | No
39 | Post-Installation | Restart Services | LRE Admin | Primary LRE Server | 1. Restart "OpenText Performance Engineering Backend" Service 2. Restart IIS | Pending | Applies configuration changes | No

## SOE - HOST Installation Steps
# | Phase | Task | Executor | Target | Detailed Steps | Status | Purpose | Completed | Notes
|  | Start - Configure TLS/SSL |  |  | Start - Configure TLS/SSL
30 | Configuration | Update LTOPSvc.exe.config | LRE Adm | Target Host Machine | 1. Create backup copy of "LTOPSvc.exe.config" file from "D:\LREHost\bin\LTOPbin" 2. Copy "LTOPSvc.exe.config-for_ssl" from "D:\LREHost\conf\httpsconfigfiles" to "D:\LREHost\bin\LTOPbin" | Pending | Enables TLS/SSL for host | Yes | D:\LREHost\bin\LTOPbin\LTOPSvc.exe.config
31 | Configuration | Restart Service | LRE Adm | Target Host Machine | Restart the "OpenText Performance Engineering Load Testing" Service | Pending | Applies TLS/SSL configuration | No
|  | End - Configure TLS/SSL |  |  | End - Configure TLS/SSL
|  | Start - Configure Server Certificates |  |  | Start - Configure Server Certificates
32 | Configuration | Update CA Certificates | LRE Adm | Target Host Machine | 1. Go to shared folder "\\rbsres01\grpareas\LRE\LREadmin\LRE_CERTS" 2. Copy content of "lre_dev_cacert.cer" file 3. Replace the content of "D:\LREHost\dat\cert\verify\cacert.cer" | Pending | Updates CA certificates with RBS Global G1 Root Proving CA | Yes | D:\LREHost\dat\cert\verify\cacert.cer
33 | Configuration | Validate Certificates | LRE Adm | Target Host Machine | Run command: "D:\LREHost\bin\gen_cert.exe -verify" | Pending | Confirms certificates are valid | No
|  | End - Configure Server Certificates |  |  | End - Configure Server Certificates

## SOE - LG Installation Steps
|  | End - LG Installation |  |  | End - LG Installation
|  | Start - Post-installation Configuration |  |  | Start - Post-installation Configuration
32 | Configuration | Update CA Certificates | LRE Adm | Target LG Machine | 1. Go to shared folder "\\rbsres01\grpareas\LRE\LREadmin\LRE_CERTS" 2. Copy content of "lre_dev_cacert.cer" file 3. Replace the content of "D:\LREOneLG\dat\cert\verify\cacert.cer" | Pending | Updates CA certificates with RBS Global G1 Root Proving CA | Yes | D:\LREOneLG\dat\cert\verify\cacert.cer
33 | Configuration | Validate Certificates | LRE Adm | Target LG Machine | 1. Open command prompt 2. Navigate to "D:\LREOneLG\bin" 3. Run command: "gen_cert.exe -verify" 4. Verify "Installed certificates verified successfully" message | Pending | Confirms certificates are valid | No
34 | Configuration | Add LG to LRE Server | LRE Adm | LRE Server | 1. Login to LRE Admin Console: https://loadrunner.webdev.banksvcs.net/admin/adminx/login 2. Navigate to "MAINTENANCE --> HOSTS" 3. Click "Add new LG" 4. Enter Host Name (e.g., DEVECPVM027762.rbsres01.network) 5. Select Host Installation: OneLG 6. Select Purpose: Load Generator | Pending | Registers LG with LRE Server | No
|  | End - Post-installation Configuration |  |  | End - Post-installation Configuration